## Free Starter Checklist
DEPLOYIQ — FREE STARTER CHECKLIST
30 essential checks from the 200+ point DeployIQ system. Full version: deployiq.contra.com
# | CHECKLIST ITEM | WHY IT MATTERS | STATUS | NOTES
STAGE 1: PROJECT INITIATION (8 of 14 checks shown)
1 | Project Intake Form completed and signed before any development begins | Signed form = documented contract. Prevents scope creep and mid-project disputes.
2 | Business question answered by this dashboard written in one clear sentence | Vague question = vague dashboard. One sentence forces clarity before development.
3 | Primary decision-maker identified by name—not just "the team" | Without a named decision-maker, every stakeholder becomes a co-designer.
4 | All stakeholders who can veto or change scope identified upfront | Hidden stakeholders discovered post-launch cause mandatory rework.
5 | Kickoff meeting held before any Power BI Desktop work begins | One 30-minute call eliminates most future scope changes.
6 | Expected delivery date agreed and documented in writing | Undocumented deadlines become moving targets.
7 | Power BI license type confirmed before workspace planning begins | License determines available features.
8 | KPIs and metrics listed and agreed in writing before development | Undocumented metrics become post-delivery disagreements.
STAGE 2: STAKEHOLDER ALIGNMENT (5 of 14 checks shown)
9 | All stakeholders have reviewed and confirmed requirements in writing | Written confirmation creates accountability.
10 | Definition of every KPI confirmed with business owner | Revenue can mean different things to different people.
11 | RLS requirement confirmed before model build | Late RLS planning costs significantly more time.
12 | User access list collected with email addresses | Sharing mistakes are costly.
13 | Dashboard ownership assigned to one named person | One person must own the dashboard after launch.
STAGE 5: DAX QUALITY (8 of 35 checks shown)
14 | DIVIDE() used for all division—not "/" | Avoid divide-by-zero errors.
15 | Every CALCULATE measure tested in multiple filter contexts | CALCULATE behaves differently across filters.
16 | Time intelligence tested using a marked Date table | Required for correct YTD and LY calculations.
17 | No hardcoded years or dates inside measures | Hardcoded dates silently fail over time.
18 | Grand totals in Matrix visuals verified manually | Executives frequently validate totals first.
19 | Percentage measures formatted as percentages | Display percentages correctly.
20 | Performance Analyzer run before UAT | Catch performance issues early.
21 | Measures tested with all slicers cleared | Default report view must work correctly.
STAGE 8: USER ACCEPTANCE TESTING (5 of 25 checks shown)
22 | UAT completed by real end users | Developers and users test differently.
23 | Revenue validated against source system | Protect stakeholder trust.
24 | RLS tested with real Service accounts | Desktop testing alone is insufficient.
25 | Clear All Filters button tested | Users need an easy reset option.
26 | UAT sign-off received before deployment | Avoid approval disputes later.
STAGE 11: DEPLOYMENT (4 of 30 checks shown)
27 | Final PBIX backed up in two locations | Ensure recovery if deployment fails.
28 | Manual refresh completed successfully after publishing | Confirms scheduled refresh readiness.
29 | Refresh failure notifications enabled | Avoid silent data failures.
30 | Production RLS verified using a real user | Final validation after deployment.
🚀 WANT THE COMPLETE SYSTEM?
This free checklist contains 30 of 200+ checks in DeployIQ.
✅ 200+ checks | vs 30 in this free version
✅ 14 complete stages | vs 5 partial stages
✅ 35+ Excel templates | Project Intake, UAT, RLS Matrix, Adoption Tracker, etc.
✅ Python Workspace Scanner | Automatically populates checklist from a Power BI workspace in about 30 seconds
✅ Worked Examples | Shows what "good" looks like with completed samples
Get DeployIQ Complete → deployiq.contra.com
DeployIQ Free Starter Checklist v1.0 © 2026 Siddhi Gupta Full system: deployiq.contra.com